## HUBs_Budget
| ILLINOIS HUB |  | NEVADA HUB |  | KENTUCKY HUB
CATEGORY | Hub Funding | Date | Hub Funding | Date | Hub Funding | Date
DATE
ORIGINAL HUB FUNDING YR1-3 | 55970.671 | 2010-09-20 | 67546.25 | 2010-09-20 | 59259.42 | 2010-08-29
Contract Exptension thru 12/31/2014 | - 0 - | 2014-04-22 | - 0 - | 2014-04-22 | - 0 - | 2014-04-23
HUB Maintenance | - 0 - | 8/2/62014 | 19190 | 2014-09-11 | 36612 | 2014-08-14
2014 GIN-Stack Contracts
State NODE | AK | AL | DE | HI | IN | MT | MI | ND | UT | WA | WI
Contract Date | 2014-10-31 | 2014-11-24 | 0 | 2014-11-17 | 2014-11-20 | 2014-11-03 | 0 | 2014-12-01 | 2014-11-06 | 2014-10-31 | 0
Funding | 9000 | 12000 | 0 | 12000 | 9000 | 12000 | 9000 | 9000 | 9000 | 12000 | 9000
Eight states (IN, UT, ND, WI, DE, TX, MI, and AK) opted to install Geoportal as a catalog server, coupled with GeoServer or ArcGIS Server for web services. Four states (MT, AL, HI, WA) decided to install GINstack software. In both cases, data services are transferred from the regional hubs back to these states to host, and the metadata for all resources submitted to NGDS hosted at the State Geothermal Data Repository is extracted and also transferred. Six additional states were already serving their own web services and continue to do so (AZ, NH, KS, MN, OR, WV).

## Training
Date | Event | HUB/NODE | Comments
2011
2011-04-11 | AZGS Webinar | AZGS | AZGS HUBS - Data and Serving Data. ALL HUBs attended.
2011-04-12 |  | AZGS | AZGS Webinar: AZGS HUBS – Data and Serving Data
2011-04-26 |  | AZGS | AZGS Webinar: AZGS HUBS – Data and Serving Data
2011-05-17 | Are Data Good | AZGS | AZGS coordinated technical webinar
2011-08-03 | HUB Workshop |  | Presentation 1: States role as a Hub
2011-08-03 | HUB Workshop |  | Presentation 2: Templates
2011-08-03 | HUB Workshop |  | Presentation 3: WMS/WFS; Setting up a service (example)
2011-08-04 | HUB Workshop |  | - Maintenance Strategy
2011-08-04 | HUB Workshop |  | - Regional Seminars and States Training
2011-12-31 | year end report | AZGS | The four regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components took place and network backup protocols were discussed. We plan to host another hub workshop in conjunction with the technical project participants workshop during the summer of 2012.
2012
March 26-29, 2012 | ESRI Workshop | IL HUB | Attended Esri Developer Summit in Palm Springs, CA
May 3-4, 2012 | One Geology Workshop | IL HUB | Attend USGIN/OneGeology US Workshop in Denver, CO
July 17-20, 2012 | ESIP Meeting | IL HUB | Attended ESIP Summer Meeting, Madison, WI
September 5-6, 2012 | AZGS Hub Meeting | KY HUB | Doug Curl. KY. Ky is running two servers that mirror each other, using F5 hardware for load balancing, fail over. Data is on a shared SAN, SAN is backed up nightly. Geothermal data is in file geodatabases, backed up via file system backup. Each state has a separate file geodatabase for their services. Geothermal activity in KY is low temperature focused, e.g. ground source heat pumps.
September 5-6, 2012 | AZGS Hub Meeting | IL HUB | Melanie Barrett, IL: nearing hardware capacity (many scanned maps in WMS services…). Nightly differential backups. Monthly full backup, no offsite DR backup. The folde containing ESRI service configurations is backed up. Most data in file geodatabases
September 5-6, 2012 | AZGS Hub Meeting | NV HUB | Gary Johnson, NV, Running a used server, not heavily loaded. No backup. Get data from Celia, put in file geodatabase for each state
September 5-6, 2012 | AZGS Hub Meeting | AZGS | Ryan – all services in SDE PostGIS db on web server, network has staging geodatabases. Set up service in Staging DB, then mirrored to live server. Staging db (SQL server) does SQL server backup; back up files are backed up. Service configurations on web server are not backed up. Using SDE in PostGres/PostGIS. To server ArcGIS data using OpenSource dB, the hard part is transforming ESRI geometry to WKB or WKT. By using SDE connection from Staging dB to PostGIS/SDE (using PostGIS geometry encoding), geometry transformation happens when ArcCatalog pushes feature classes into PostGIS
September 5-6, 2012 | AZGS Hub Meeting | HUBs | Service contracts
September 5-6, 2012 | AZGS Hub Meeting | HUBs | System operations cost
September 5-6, 2012 | AZGS Hub Meeting / 10:00 BSU NGDS Design weekly teleconference | AZGS | Discussion of Node in a Box functionality, Repository migration, Migration to ArcGIS 10.1, Backup/Disaster recovery plan, Work plan - investigate cloud storage - Virtualize hub servers using HyperV 2012
2013
2013-05-13 | HUB Workshop | NV HUB | Regional workshop at the Grand Sierra Resort in Reno, NV
2013-05-14 | HUB Workshop | NV HUB | Attended the West Coast Project Workshop in Reno, NV
July 25-26, 2013 |  | IL HUB | Arrangements made for Eastern States Geothermal Workshop in Urbana-Champaign
2013 4th Quarter | HUB Workshop | KY HUB/IL HUB | KGS co-hosted a workshop with the IGS at their location. This was be for the states in our regions. | Need exact date from Christy?
2013 4th Quarter | VA Workshop | KY HUB | Also attended a workshop hosted by the Virginia Geological Survey to discuss with their states how they are preparing data. Gave a presentation on KY HUB role. | Need exact date from Christy?

## By_Qtrs
DATE | HUB | Comments/Activities
2010 2nd Quarter
2010-05-04 | AZGS | Project was formally launched
2010-05-01 | AZGS | Hubs operational for hosting of WMS, WFS and document repository services
April – June, 2010 | AZGS | Acquired or ordered all hardware necessary for project personnel at AZGS
April – June, 2010 | AZGS | Plans for regional hub activities were formalized in a telephone conference with technical personnel from each hub partner (NV, IL, KY), and a template for the regional hub Statement of Work was produced and distributed. All regional centers have ArcGIS server 9.3 available, and we will initially use this platform for deploying WMS, WFS, KML and ESRI map and data services.
2010 4th Quarter
2010 | year end report | Plans for the regional server and training hubs were developed in collaboration with the hub organizations (NV, KY, IL).
2010 | year end report | Preparation for AZGS to serve as data hub
2010 | year end report | Network rewiring, firewall and switch upgrades
2010 | year end report | Server upgrades and move to archival quality server room at AZGS
2010 | year end report | Scanners acquired to digitize AZ & CA data collection
2011 1st Quarter
2011 1st Quarter | IL HUB | Participated in AZGS coordinated technical webinars on metadata, boreohole temperature data, and serving data.
2011 1st Quarter | IL HUB | Installed hub server.
2011 1st Quarter | IL HUB | Published WMS service using Illinois borehole temperature data as example for data serving webinar.
2011 2nd Quarter
2011 2nd Quarter | NV HUB | Work will continue on to fully establish the Western Hub
2011 2nd Quarter | IL HUB | Participated in AZGS coordinated technical webinar "Are Data Good?" on May 17, 2011 Organized list of contacts from States in Illinois Hub region. Prepared directory structure and mechanism for handling and tracking data received from States in anticipation of eventual data deliveries. Corresponded with the State of Vermont on data (georeferenced maps).
2011 3nd Quarter
2011 3nd Quarter | KY HUB | KY HUB provided services to host data posted by Louisianna.
2011 3nd Quarter | IL HUB | Began hosting of data services from states in IL HUB region, enforcing consistent handling and processing of data from data receipt to service publishing. Documented procedures to support above tasks. Attended AZGS hosted Hub Workshop in Tucson, AZ with other Hub representatives.
2011 4th Quarter
2011 4th Quarter | IL HUB | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Helped states get data into content templates or to load data into content schema.
2011 | year end report | Regional server and IT HUBs established; including a workshop for hub managers at AZGS to discuss technical requirements and backup requirements for the system.
2011 | year end report | The four regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components took place and network backup protocols were discussed. We plan to host another hub workshop in conjunction with the technical project participants workshop during the summer of 2012.
2012 1st Quarter
2012 1st Quarter | IL HUB | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Helped states get data into content templates or to load data into content schema. Worked with AZGS to ensure that hosted data services were valid. Update and redeploy services as requested by AZGS.
2012 2nd Quarter
2012 2nd Quarter | IL HUB | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Update and redeploy services as requested by AZGS. Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer).
2012 2nd Quarter | NV HUB | Files from WA, ID and OR (along w/numerous NV files) were added to map services on the hub. Search capabilities added and data acquisition from multiple states and data sets was programmed. Updated the Nevada Hub to include the Idaho data. New interactive map features allow one to identify any feature, turn off layers, extract any state’s data, or extract all data of one type or another, or all the data hosted by the NV HUB.
2012 2nd Quarter | KY HUB | Work continued with deployment of services and file hosting for states within the KY HUB designated states.
2012 3rd Quarter
2012 3rd Quarter | IL HUB | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on Illinois hub web server. Updated and redeployed services as requested by AZGS. Validated all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer).
2012 3rd Quarter | KY HUB | Implemented FOSS OGCvia ArcGIS Server. ArcGIS In Place - 2 server architecture.
2012 3rd Quarter | KY HUB | Created ArcGIS Server/OGC services for states within the KY Hub area. Provided hosting for scanned images on the HUB webserver for TN, AR, LA, FL, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as they are received.
2012 3rd Quarter | KY HUB | At HUB meeting in Arizona in Sept, discussed hosting a workshop for the HUB states at each HUB survey - assisted by the AZ Geological Survey staff. Still in the early planning stages of this activity.
2012 3rd Quarter | KY HUB | Attended HUB workshop meeting in Tuscon, AZ. Much of the focus was planning for sustainability with server architecture.
2012 3rd Quarter | NV HUB | Files from WA, ID , MT and OR (along w/numerous NV files) were added to map services on the NV HUB. Search capabilities added and data acquisition from multiple states and data sets was programmed. NV HUB to include the ID, MT, WA, NV data. New map features allow one to identify any feature, turn off layers, extract any state’s data, or extract all data of one type or another, or all the data hosted by the NV HUB. Updated the functionality of the NV HUB web application. Also added Scanned documents to the NV HUB from Wyoming that do not appear on the Web application.
2012 4th Quarter
2012 4th Quarter | IL HUB | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on Illinois hub web server. Update and redeploy services as requested by AZGS. Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer). Attended conference call with AZGS and hub technical leads to discuss future plans. Develop python scripts to migrate existing services, and publish new services from ArcGIS Server 10 to ArcGIS Server 10.1.
2012 4th Quarter | KY HUB | Created ArcGIS Server/OGC services for states within the KY HUB area. Provided hosting for scanned images on the HUB webserver for AR, DE, FL, GA, LA, MD, SC, TN, and VA. Received content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and provided services as data are received. During this period one new service (SCSeismicHypocenters) was created - mostly received updates to data from the AZGS for existing services.
2012 4th Quarter | KY HUB | Participated in a webinar to discuss HUB workshop plans. KGS is planning to host a workshop with the IGS at their location. This will be for the states in our regions. A workshop will also be hosted in Reno - plans are still tentative on these.
2012 | AZGS Peer Review | Data made accessible online through web-accessible data providers. Hubs (AZ, NV, IL, KY) available for backup or providing service. All hubs operational and serving data in FY 2011. AASG nodes and hubs linked with the DOE GDR, OpenEI, and other NGDS nodes. Site visits to NREL. Technical Collaboration and Review visits with Boise State Univ (NGDS Design-Build team)
2013 2nd Quarter
2013 2nd Quarter | KY HUB | Created ArcGIS Server/OGC services for states within the KY HUB area. Provided hosting for scanned images on the HUB webserver for DE, GA, MD, TN, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as data are received. Setup or updated 8 services during this period for DE, GA, AR, FL, KY, TN, and VA.
2013 2nd Quarter | KY HUB | 58 total services hosted so far. 3 services taken offline (for WV) because state is now hosting their own.
2013 2nd Quarter | IL HUB | Map document published as Mapping/WMS/WFS/KML, map document- and service-level metadata populated, and service validated against appropriate schema definition file. Files of various formats posted on server and resource_url field populated in metadata document. Links in metadata validated.
2013 2nd Quarter | IL HUB | Hosting servies and data for 12 states: CT, IL, IN, IA, ME,MA, MO, NH, NJ, OH, PA, RI
2013 2nd Quarter | NV HUB | Added web services for ID, NV, UT and MT as requested by AZGS. Purchased the new server and installed Web services software. Installed backup software. Created a virtual server, and sent an image of the server to AZGS for testing. Maintained the web services. Coordinated with AZGS for the regional workshop scheduled for May 13, 2013 at the Grand Sierra Resort in Reno NV.
2013 3rd Quarter
2013 3rd Quarter | IL HUB | Executed budget revision and new contract end date for hub activities(4/30/2014). QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on Illinois hub web server. Append, update, replace, and redeploy services as requested by AZGS. Begin testing Excel to NGDS dataset conversion tool supplied by AZGS. Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (WFS Validator). Acquired new server for use in virtualized environment, and for mirroring another regional hub.
2013 3rd Quarter | NV HUB | Worked on updating States data submitted by AZGS to the NV HUB. NV HUB’s server went down due to power outages at the university on June 18th , so Gary Johnson spent the remainder of the month setting up the new server’s virtual server (WEB3VM) , along with moving all data to the new server and started installing new web services for each state. Restored the NV HUB's Server after power outage took out the RAID5 data storage. Continued working on submitted web services from AZGS on the NV HUB.
2013 4th Quarter
2013 4th Quarter | IL HUB | Hosting services and data for 3 additional states: NY, VT, MI
2013 4th Quarter | NV HUB | Continued work on a virtual server. Maintained the web services. Worked with Ron Palmer to create replication from the NV HUB and AZGS. Tested replication. (Completed and submitted). Worked on updating State's data submitted by AZGS to the NV HUB. Added 30 new or appended datasets to the NV HUB from other states for a total number of services to 40: CO (5), ID (6), MT (6), NV (6), SD (3), UT (12), WY (2). Continue to update the NV HUB main server (Web3.rd.unr.edu) and the virtual server (Web3vm.rd.unr.edu). Continued updating the NV_HUB web applications.
2013 4th Quarter | KY HUB | Created ArcGIS Server/OGC services for states within the KY Hub area. Provided hosting for scanned images on the HUB webserver for DE, GA, MD, TN, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as they are received. Setup or updated numerous services during this period for AL, AR, DE, GA, FL, KY, NC, SC, TN, and VA. In-Progress - still receiving content models from AZGS for HUB states. 79 total services hosted to date.

## HUB Tasks
Disaster recovery Hyper V replication
Virtualized server deployment
Hubs Tasks per contract:
Task 1. Implement ArcGIS server
Verify that ArcGIS server is operational by implementing a map service using vector data for a geologic map to make the map available via ArcGIS map service, OGC WMS 1.3.0, and WFS 1.1.0
Task 2. Implement FOSS OGC service provider
Verify that GeoServer, a free, open-source GIS server, is operational by implementing a map service using vector data for a geologic map to make the map available via OGC WMS 1.3.0 and WFS 1.1.0.
Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration
Subtask 1: Data hosting. The HUBs will make server resources available for hosting and serving data from other project participants in their region, and assist with data preparation and service deployment
Subtask 2: Technical assistance and training. One FTE will be available for NGDS data development support, and requests for help will be handled on a first come-first serve basis.
Subtask 3: Metadata workflow development and training. The HUBs will also train project participants in procedures to develop minimum metadata required to register resources with the National Geothermal Data System.
Task 4. Host workshop on service implementation using platforms hosted by Kentucky Geological Survey
Will host at least one regional workshop for project participants in the region for hands on technical training on server implementation, data preparation, and service deployment using ESRI or FOSS software, determined based on input from regional project participants. The first workshop will be held between April 2011 and June 2011.
Task 5. Participate in AASG NGDS-data project technical conference calls
Project technical personnel will participate in technical conference call to be arranged and hosted by AZGS, and contribute to system problem solving and debugging efforts
Budget period has been extended to December 31, 2014 to maintain services at the HUBs.
Task 6. Supplemental Funding for Hub Maintenance
Purchase and preparation of a PowerEdge T260 Server
Preparation and implementation of a virtual server and disaster recovery plan
Transfer of existing data to the new server
Assist with the transfer of data from the Hub to GIN-stack installers
Travel to one final Hub Meeting, location TBD

## By_HUB
IL HUB
| Task 1. Implement ArcGIS server | 2011 1st Quarter | Installed hub server.
| Task 1. Implement ArcGIS server | 2011 1st Quarter | Published WMS service using Illinois borehole temperature data as example for data serving webinar.
| Task 2. Implement FOSS OGC service provider | 2011 2nd Quarter | Organized list of contacts from States in Illinois Hub region. Prepared directory structure and mechanism for handling and tracking data received from States in anticipation of eventual data deliveries. Corresponded with the State of Vermont on data (georeferenced maps).
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2011 3nd Quarter | Began hosting of data services from states in IL HUB region, enforcing consistent handling and processing of data from data receipt to service publishing. Documented procedures to support above tasks.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2011 4th Quarter | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Helped states get data into content templates or to load data into content schema. | QA/QC data during continued service creation. Assisted states to use content schema.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 1st Quarter | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Helped states get data into content templates or to load data into content schema. Worked with AZGS to ensure that hosted data services were valid. Update and redeploy services as requested by AZGS. | Worked with AZGS to ensure hosted data services were valid. Update and redeployed services as needed.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 2nd Quarter | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on IL HUB web server. Update and redeploy services as requested by AZGS. Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer). | Begin to validate new services using schema definition files (.xsd) and validation workflow and tools (XMLExplorer).
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 3rd Quarter | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on Illinois hub web server. Updated and redeployed services as requested by AZGS. Validated all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer).
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 4th Quarter | QA/QC of data during service creation. Continued service creation and hosting of data files from web accessible folders on Illinois hub web server. Update and redeploy services as requested by AZGS. Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (XMLExplorer). Attended conference call with AZGS and hub technical leads to discuss future plans. Developed python scripts to migrate existing services, and publish new services from ArcGIS Server 10 to ArcGIS Server 10.1. | Developed python scripts to migrate and publish services from ArcGIS Server 10 to ArcGIS Server 10.1.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 2nd Quarter | Map document published as Mapping/WMS/WFS/KML, map document- and service-level metadata populated, and service validated against appropriate schema definition file. Files of various formats posted on server and resource_url field populated in metadata document. Links in metadata validated. | Maps published as Mapping/WMS/WFS/KML, map document and service-level metadata populated, and service validated against schema definition file. Links in metadata validated.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 2nd Quarter | Hosting servies and data for 12 states: CT, IL, IN, IA, ME,MA, MO, NH, NJ, OH, PA, RI
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 3rd Quarter | QA/QC of data during service creation.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 4th Quarter | Continued service creation and hosting of data files from web accessible folders on Illinois hub web server.
| Task 4. Host workshop on service implementation using platforms hosted by Kentucky Geological Survey | July 25-26, 2013 | Eastern States Geothermal Workshop in Urbana-Champaign
| Task 5. Participate in AASG NGDS-data project technical conference calls | 2011 1st Quarter | Participated in AZGS coordinated technical webinars on metadata, borehole temperature data, and serving data.
| Task 5. Participate in AASG NGDS-data project technical conference calls | 2011 2nd Quarter | Participated in AZGS coordinated technical webinar "Are Data Good?" on May 17, 2011
| Task 5. Participate in AASG NGDS-data project technical conference calls | July 17-20, 2012 | Begin testing Excel to NGDS dataset conversion tool supplied by AZGS.
| Task 5. Participate in AASG NGDS-data project technical conference calls | July 25-26, 2013 | Validate all new services using schema definition files (.xsd) and recommended validation workflow and tools (WFS Validator).
| Task 5. Participate in AASG NGDS-data project technical conference calls | March 26-29, 2012 | ESRI Workshop: Arrangements made for Eastern States Geothermal Workshop in Urbana-Champaign
| Task 5. Participate in AASG NGDS-data project technical conference calls | May 3-4, 2012 | One Geology Workshop: Attend USGIN/OneGeology US Workshop in Denver, CO
| Task 5. Participate in AASG NGDS-data project technical conference calls | September 5-6, 2012 | AZGS Hub Meeting: Melanie Barrett, IL: nearing hardware capacity (many scanned maps in WMS services…). Nightly differential backups. Monthly full backup, no offsite DR backup. The folder containing ESRI service configurations is backed up. Most data in file geodatabases | AZGS Hub Meeting: IL HUB nearing hardware capacity. Backups perofrmed nightly, monthly (full) but no offsite DR backup.
| Task 6. Supplemental Funding for Hub Maintenance | 2013 3rd Quarter | Acquired new server for use in virtualized environment, and for mirroring another regional hub. | Acquired new server for virtualized environment and mirroring another regional hub.
KY HUB
| Task 1. Implement ArcGIS server | 2012 3rd Quarter | Implemented FOSS OGCvia ArcGIS Server. ArcGIS In Place - 2 server architecture.
| Task 2. Implement FOSS OGC service provider | 2012 3rd Quarter | Created ArcGIS Server/OGC services for states within the KY Hub area. Provided hosting for scanned images on the HUB webserver for TN, AR, LA, FL, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as they are received. | Created ArcGIS Server/OGC services. Hosting scanned images on the HUB webserver for TN, AR, LA, FL, and VA. Content models and .mxd services aprovided.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2011 3nd Quarter | KY HUB provided services to host data posted by LA.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 2nd Quarter | Work continued with deployment of services and file hosting for states within the KY HUB designated states. | Continued deployment of services and file hosting.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 4th Quarter | Created ArcGIS Server/OGC services for states within the KY HUB area. Provided hosting for scanned images on the HUB webserver for AR, DE, FL, GA, LA, MD, SC, TN, and VA. Received content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and provided services as data are received. During this period one new service (SCSeismicHypocenters) was created - mostly received updates to data from the AZGS for existing services. | Created ArcGIS Server/OGC services. Provided hosting data for AR, DE, FL, GA, LA, MD, SC, TN, and VA. Content models and .mxd services provided. New services and updates to existing data.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 2nd Quarter | Created ArcGIS Server/OGC services for states within the KY HUB area. Provided hosting for scanned images on the HUB webserver for DE, GA, MD, TN, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as data are received. Setup or updated 8 services during this period for DE, GA, AR, FL, KY, TN, and VA. | Provided hosting for data for DE, GA, MD, TN, and VA. Setup or updated 8 services during this period for DE, GA, AR, FL, KY, TN, and VA.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 2nd Quarter | 58 total services hosted so far. 3 services taken offline (for WV) because state is now hosting their own. | Total of 58 services hosted. 3 services taken offline (for WV) for state hosting own data.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 4th Quarter | Created ArcGIS Server/OGC services for states within the KY Hub area. Provided hosting for scanned images on the HUB webserver for DE, GA, MD, TN, and VA. Receiving content templates (spreadsheets) and .mxd with personal geodatabases from AZGS and providing services as they are received. Setup or updated numerous services during this period for AL, AR, DE, GA, FL, KY, NC, SC, TN, and VA. In-Progress - still receiving content models from AZGS for HUB states. 79 total services hosted to date. | Setup or updated services for AL, AR, DE, GA, FL, KY, NC, SC, TN, and VA. Total 79 services hosted to date.
| Task 4. Host workshop on service implementation using platforms hosted by Kentucky Geological Survey | 2013 4th Quarter | KGS co-hosted a workshop with the IGS at their location. This was be for the states in our regions. | KGS co-hosted a workshop with the IGS
| Task 4. Host workshop on service implementation using platforms hosted by Kentucky Geological Survey | 2013 4th Quarter | Also attended a workshop hosted by the Virginia Geological Survey to discuss with their states how they are preparing data. Gave a presentation on KY HUB role. | Attended a workshop hosted by the Virginia Geological Survey. Gave a presentation on KY HUB role.
| Task 5. Participate in AASG NGDS-data project technical conference calls | 2012 3rd Quarter | At HUB meeting in Arizona in Sept, discussed hosting a workshop for the HUB states at each HUB survey - assisted by the AZ Geological Survey staff. Still in the early planning stages of this activity. | HUB meeting in Arizona in Sept. Focus on planning for sustainability with server architecture.
|  | 2012 3rd Quarter | Attended HUB workshop meeting in Tuscon, AZ. Much of the focus was planning for sustainability with server architecture.
|  | 2012 4th Quarter | Participated in a webinar to discuss HUB workshop plans. KGS is planning to host a workshop with the IGS at their location. This will be for the states in our regions. A workshop will also be hosted in Reno - plans are still tentative on these. | Participated in a webinar to discuss HUB workshops.
| Task 6. Supplemental Funding for Hub Maintenance | September 5-6, 2012 | Doug Curl. KY. Ky is running two servers that mirror each other, using F5 hardware for load balancing, fail over. Data is on a shared SAN, SAN is backed up nightly. Geothermal data is in file geodatabases, backed up via file system backup. Each state has a separate file geodatabase for their services. | Running two servers that mirror each other, using F5 hardware for load balancing, fail over. Data is on a shared SAN, SAN is backed up nightly.
NV HUB
| Task 1. Implement ArcGIS server | 2011 2nd Quarter | Work will continue on to fully establish the Western Hub | Work continues to fully establish the Western Hub
| Task 2. Implement FOSS OGC service provider | 2011 2nd Quarter | Work will continue on to fully establish the Western Hub
| Task 2. Implement FOSS OGC service provider | 2013 3rd Quarter | NV HUB’s server went down due to power outages at the university on June 18th , so Gary Johnson spent the remainder of the month setting up the new server’s virtual server (WEB3VM) , along with moving all data to the new server and started installing new web services for each state. Restored the NV HUB's Server after power outage took out the RAID5 data storage. Continued working on submitted web services from AZGS on the NV HUB. | Server down due to power outages at the university on June 18th , spent the remainder of the month setting up the new server’s virtual server (WEB3VM). Moved all data to the new server and started installing new web services. Restored the NV HUB's Server after power outage.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 2nd Quarter | Files from WA, ID and OR (along w/numerous NV files) were added to map services on the hub. Search capabilities added and data acquisition from multiple states and data sets was programmed. Updated the Nevada Hub to include the Idaho data. New interactive map features allow one to identify any feature, turn off layers, extract any state’s data, or extract all data of one type or another, or all the data hosted by the NV HUB. | Data from ID, NV, OR, and WA added to map services. Search capabilities added and data acquisition was programmed. New interactive map features data hosted by the NV HUB.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2012 3rd Quarter | Files from WA, ID , MT and OR (along w/numerous NV files) were added to map services on the NV HUB. Search capabilities added and data acquisition from multiple states and data sets was programmed. NV HUB to include the ID, MT, WA, NV data. New map features allow one to identify any feature, turn off layers, extract any state’s data, or extract all data of one type or another, or all the data hosted by the NV HUB. Updated the functionality of the NV HUB web application. Also added Scanned documents to the NV HUB from Wyoming that do not appear on the Web application. | Updated the functionality of the NV HUB web application. Added data from WY not on the Web application.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 2nd Quarter | Added web services for ID, NV, UT and MT as requested by AZGS. Purchased the new server and installed Web services software. Installed backup software. Created a virtual server, and sent an image of the server to AZGS for testing. Maintained the web services. Coordinated with AZGS for the regional workshop scheduled for May 13, 2013 at the Grand Sierra Resort in Reno NV. | Added web services for ID, NV, UT and MT. Purchased the new server and installed Web services software. Installed backup software. Created a virtual server. Maintained the web services. Coordinated for the regional workshop scheduled for May 13, 2013 at the Grand Sierra Resort in Reno NV.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 3rd Quarter | Worked on updating States data submitted by AZGS to the NV HUB. | Updated States data and services.
| Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration | 2013 4th Quarter | Worked on updating State's data submitted by AZGS to the NV HUB. Added 30 new or appended datasets to the NV HUB from other states for a total number of services to 40: CO (5), ID (6), MT (6), NV (6), SD (3), UT (12), WY (2). | Updated States data and services. Added 30 new or appended datasets for CO, ID, MT, NV, SD, UT, WY for a total of 40 services.
| Task 4. Host workshop on service implementation using platforms | 2013-05-13 | Regional workshop at the Grand Sierra Resort in Reno, NV
| Task 5. Participate in AASG NGDS-data project technical conference calls | September 5-6, 2012 | Gary Johnson, NV, Running a used server, not heavily loaded. No backup. Get data from Celia, put in file geodatabase for each state | Running a used server, not heavily loaded. No backup. Data put in file geodatabases for each state.
| Task 5. Participate in AASG NGDS-data project technical conference calls | 2011-08-01 | The four regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components took place and network backup protocols were discussed. We plan to host another hub workshop in conjunction with the technical project participants workshop during the summer of 2012. | HUBs meeting in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components and network backup protocols were discussed.
| Task 5. Participate in AASG NGDS-data project technical conference calls | 2011-04-11 | AZGS HUBS - Data and Serving Data. ALL HUBs attended. | Attended AZGS webinar: HUBS - Data and Serving Data.
| Task 6. Supplemental Funding for Hub Maintenance | 2013 4th Quarter | Continued work on a virtual server. Maintained the web services. Continue to update the NV HUB main server (Web3.rd.unr.edu) and the virtual server (Web3vm.rd.unr.edu). Continued updating the NV_HUB web applications. | Continued work on a virtual server. Maintained web services. Continue to update the main server and the virtual server. Continued updating web applications.
| Task 6. Supplemental Funding for Hub Maintenance | 2013 4th Quarter | Worked with Ron Palmer to create replication from the NV HUB and AZGS. Tested replication. (Completed and submitted). | Worked with AZGS to create replication from the NV HUB and AZGS. Tested replication. (Completed and submitted).
AZ HUB/AZGS
| Task 1. Implement ArcGIS server | 2011 | Data made accessible online through web-accessible data providers. Hubs (AZ, NV, IL, KY) available for backup or providing service. All hubs operational and serving data in FY 2011. AASG nodes and hubs linked with the DOE GDR, OpenEI, and other NGDS nodes.
mssing info | Task 2. Implement FOSS OGC service provider | 2010 4th quarter | A prototype catalog using ESRI Geoportal implemented and configured. Metadata from USGIN Geonetwork Open Source catalog prototype harvested. Deployed the system catalog node at AZGS using the ESRI Geoportal.
|  | 2011 1st quarter | Storage Area Network (SAN) set up at AZGS to handle data for the NGDS and as prototype for SANs at network hubs (NV, KY, IL).
mssing info |  | 2010 4th quarter | Prototype Web services (WFS and WMS) were deployed using the AASG geothermal data Well Header template
|  | 2010 4th quarter | AZGS hosted a two-day workshop on the ESRI Geoportal software
|  | 2012 4th quarter | New application developed (NGDS Feature Search & Map Viewer) and 2 applications upgraded (Catalog Search Client and ArcMap Client).
|  | 2012 4th quarter | Multiple NGDS nodes delivering data live in an operational prototype network. Nodes include the hub states and states that are self-serving data.
|  | 2013 1st quarter | Completed a manual replication test between the AZGS hub and the NV hub
|  | 2013 1st quarter | Quarterly conference call with the regional server hub managers (IL, KY, and NV). Topics included progress on virtualization and recovery plan.
|  | 2013-05-14 | Hosted our first regional workshop in Reno, Nevada in conjunction with NV GIS Conference. Attendees were West Coast states (UT, ID, WA, NV, NM and ND)
|  | 2013 2nd quarter | QA-QC testing of service URLs, online file/server locations, and online applications hosted by Hubs or self-serving states to ensure distibution working properly.
|  | 2013 3rd quarter | Worked with NV, IL, and KY HUBs to provide cloud-based replication. Tested deployment of node-in-a-box at AASG project site (through the BSU Design/Test project).
|  | 2013 3rd quarter | Successfully recovered the NV hub based on established documentation and protocols.
|  | 2013 4th quarter | Participated in meetings with NGDS Design & Testing project and began development cycle for CKAN based repository and data entry software. Continue to add subrecipient data to the AASG catalog after QA/QC.
|  | 2014 1st quarter | Continue to work with USGS National Map, Geothermal Prospector, and IRENA Global Atlas to use NGDS services in their portals.
|  | 2014 1st quarter | Finalize revisions/clean-up on main project websites, integrating CKAN NGDS aggregator node with geothermalData.org site. Work with NGDS Design & Testing team to complete user documentation.
|  | 2014 2nd quarter | Continue to add sub recipient data to system as partners update existing datasets or submit new ones.
|  | 2014 3rd quarter | Harvest additional deployed nodes which will come online for at least 8 states to install GIN Stack.
Task 3. Host data for other surveys in the region as requested, and assist with data preparation, service deployment, and metadata registration
| Task 4. Host workshop on service implementation using platforms | 2011-04-11 | AZGS HUBS - Data and Serving Data. ALL HUBs attended. | AZGS webinar: HUBS - Data and Serving Data. ALL HUBs attended.
| Task 4. Host workshop on service implementation using platforms | 2011-04-12 | AZGS Webinar: AZGS HUBS – Data and Serving Data
| Task 4. Host workshop on service implementation using platforms | 2011-04-26 | AZGS Webinar: AZGS HUBS – Data and Serving Data
| Task 4. Host workshop on service implementation using platforms | 2011-05-17 | AZGS coordinated technical webinar: Are Data Good?
| Task 4. Host workshop on service implementation using platforms | 2011-08-03 | HUB Workshop: The four regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components took place and network backup protocols were discussed. Presentation 1: States role as a Hub; Presentation 2: Templates ; Presentation 3: WMS/WFS; Setting up a service (example) | HUB Workshop: Regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Focus on extensive training on network components and network backup protocols.
| Task 4. Host workshop on service implementation using platforms | 2011-08-04 | HUB Workshop: Maintenance Strategy and Regional Seminars and States Training
| Task 5. Participate in AASG NGDS-data project technical conference calls | September 5-6, 2012 | AZGS Hub Meeting: All services in SDE PostGIS db on web server, network has staging geodatabases. Set up service in Staging DB, then mirrored to live server. Staging db (SQL server) does SQL server backup; back up files are backed up. Service configurations on web server are not backed up. Using SDE in PostGres/PostGIS. To server ArcGIS data using OpenSource dB, the hard part is transforming ESRI geometry to WKB or WKT. By using SDE connection from Staging dB to PostGIS/SDE (using PostGIS geometry encoding), geometry transformation happens when ArcCatalog pushes feature classes into PostGIS | AZGS Hub Meeting: Services in SDE PostGIS db on web server, network has staging geodatabases. Set up service in Staging DB, then mirrored to live server. Staging db (SQL server) does SQL server backup; backed up files. Service configurations on web server not backed up.
| Task 5. Participate in AASG NGDS-data project technical conference calls | September 5-6, 2012 | AZGS Hub Meeting: Discussion of Node in a Box functionality, Repository migration, Migration to ArcGIS 10.1, Backup/Disaster recovery plan, Work plan - investigate cloud storage - Virtualize hub servers using HyperV 2012 | AZGS Hub Meeting: Discussion of Node in a Box functionality, Repository migration, Migration to ArcGIS 10.1, Backup/Disaster recovery plan, Work plan - investigate cloud storage - Virtualize hub servers using HyperV 2012
mssing info | Task 6. Supplemental Funding for Hub Maintenance

## HUBS_Timeline
HUB Deployment Timeline
| 2nd Qtr 2010 | 3rd Qtr 2010 | 4th Qtr 2010 | 1st Qtr 2011 | 2nd Qtr 2011 | 3rd Qtr 2011 | 4th Qtr 2011 | 1st Qtr 2012 | 2nd Qtr 2012 | 3rd Qtr 2012 | 4th Qtr 2012 | 1st Qtr 2013 | 2nd Qtr 2013 | 3rd Qtr 2013 | 4th Qtr 2013 | 1st Qtr 2014 | 2nd Qtr 2014 | 3rd Qtr 2014 | 4th Qtr 2014
AZGS HUB | Acquired computer/hardware for AZGS project. Formalized plans for HUB activities.Regional centers all have ArcGIS server 9.3 available. | Hardware increased to 8Tb capacity (expandible to 20Tb) for hosted data. | A prototype catalog using ESRI Geoportal implemented and configured. Metadata from USGIN Geonetwork Open Source catalog prototype harvested. Deployed the system catalog node at AZGS using the ESRI Geoportal. | Storage Area Network (SAN) set up at AZGS to handle data for the NGDS and as prototype for SANs at network hubs (NV, KY, IL). | AZGS webinar: HUBS - Data and Serving Data. All HUBs attended. | HUB Workshop: Regional hubs (AZ, NV, IL, and KY) met in early August to discuss expectations, protocols, and sustainability of the network. Focus on extensive training on network components and network backup protocols. | All hubs operational and serving data in FY 2011. AASG nodes and hubs linked with the DOE GDR, OpenEI, and other NGDS nodes. | Continue hosting data services from regional states. | Continue hosting data services from regional states. | AZGS Hub Meeting: Discussion of Node in a Box functionality, Repository migration, Migration to ArcGIS 10.1, Backup/Disaster recovery plan, Work plan - investigate cloud storage - Virtualize hub servers using HyperV 2012 | New application developed (NGDS Feature Search & Map Viewer) and 2 applications upgraded (Catalog Search Client and ArcMap Client). | Completed a manual replication test between the AZGS hub and the NV hub | Hosted our first regional workshop in Reno, Nevada in conjunction with NV GIS Conference. Attendees were West Coast states (UT, ID, WA, NV, NM and ND) | Worked with NV, IL, and KY HUBs to provide cloud-based replication. Tested deployment of node-in-a-box at AASG project site (through the BSU Design/Test project). | Participated in meetings with NGDS Design & Testing project and began development cycle for CKAN based repository and data entry software. Continue to add subrecipient data to the AASG catalog after QA/QC. | Continue to work with USGS National Map, Geothermal Prospector, and IRENA Global Atlas to use NGDS services in their portals. | Budget period has been extended to December 31, 2014 to maintain services at the HUBs. | All participating nodes continue to upload data via their node’s CSW endpoints.
|  |  | Prototype Web services (WFS and WMS) were deployed. |  | AZGS coordinated technical webinar: Are Data Good? | HUB Workshop: Maintenance Strategy and Regional Seminars and States Training |  |  |  |  | Multiple NGDS nodes delivering data live in an operational prototype network. Nodes include the hub states and states that are self-serving data. | Quarterly conference call with the regional server hub managers (IL, KY, and NV). Topics included progress on virtualization and recovery plan. | QA-QC testing of service URLs, online file/server locations, and online applications hosted by Hubs or self-serving states to ensure distibution working properly. | Successfully recovered the NV hub based on established documentation and protocols. |  | Finalize revisions/clean-up on main project websites, integrating CKAN NGDS aggregator node with geothermalData.org site. Work with NGDS Design & Testing team to complete user documentation. | Continue to add sub recipient data to system as partners update existing datasets or submit new ones.
|  |  | AZGS hosted 2-day workshop on ESRI Geoportal software | [13 empty] | Harvest additional deployed nodes which will come online for at least 8 states to install GIN Stack.
IL HUB |  |  | Purchase Oracle's Internet Devleoper software | Purchased 3 Optiplex PCs and Monitors | Purchased Optiplex Minitower,storage, and HUB server. | Began hosting of data services from states | QA/QC data during continued service creation. Assisted states to use content schema. | Purchased laptop computer. | Begin to validate new services using schema definition files (.xsd) and validation workflow and tools (XMLExplorer). | Purchased HUB Server. | Developed python scripts to migrate and publish services from ArcGIS Server 10 to ArcGIS Server 10.1. | Purchased digital scanner. | Purchased HUB server. | Maps published as Mapping/WMS/ WFS/KML, map document and service-level metadata populated, and service validated against schema definition file. Links in metadata validated. | Continued to host new data for regional states. |  | Budget period has been extended to December 31, 2014 to maintain services at the HUBs.
|  |  |  | IL HUB server installed. Published first WMS service. | Organized states contacts and prepared directory structure and mechanism for handling and tracking data |  |  | Worked with AZGS to ensure hosted data services were valid. Update and redeployed services as needed. | Provided services to host data for ME, VT, . | Continued to host new data for regional states. |  | Continued to host new data for regional states. | Continued to host new data for regional states. | Hosting services and data for 12 states: CT, IL, IN, IA, ME,MA, MO, NH, NJ, OH, PA, RI
[5 empty] | Attended AZGS webinar: HUBS - Data and Serving Data. |  |  | Provided services to host data for MA. |  | Begin testing Excel to NGDS dataset conversion tool supplied by AZGS. |  |  |  | Acquired new server for virtualized environment and mirroring another regional hub.
|  |  |  | Participated in AZGS technical webinars on metadata, borehole temperature data, and serving data. | Participated in AZGS coordinated technical webinar "Are Data Good?" on May 17, 2011 |  |  | ESRI Workshop: Arrangements made for Eastern States Geothermal Workshop in Urbana-Champaign | One Geology Workshop: Attend USGIN/OneGeology US Workshop in Denver, CO | AZGS Hub Meeting: IL HUB nearing hardware capacity. Backups perofrmed nightly, monthly (full) but no offsite DR backup. |  |  |  | Eastern States Geothermal Workshop in Urbana-Champaign
KY HUB | [5 empty] | Implemented FOSS OGCvia ArcGIS Server. ArcGIS In Place - 2 server architecture. |  | Provided services to host data for AL, AR, DE, GA, MD, and VA. | Continued deployment of services and file hosting. | Created ArcGIS Server/OGC services. Hosting scanned images on the HUB webserver for TN, AR, LA, FL, and VA. Content models and .mxd services provided. | Created ArcGIS Server/OGC services. Provided hosting data for AR, DE, FL, GA, LA, MD, SC, TN, and VA. Content models and .mxd services provided. New services and updates to existing data. |  | Provided hosting for data for DE, GA, MD, TN, and VA. Setup or updated 8 services during this period for DE, GA, AR, FL, KY, TN, and VA. | Total of 58 services hosted. 3 services taken offline (for WV) for state hosting own data. | Setup or updated services for AL, AR, DE, GA, FL, KY, NC, SC, TN, and VA. Total 79 services hosted to date. | Acquired and installed new server for serving regional hub map services and data | Budget period has been extended to December 31, 2014 to maintain services at the HUBs. | Acquired new server for virtualized environment and mirroring another regional hub
[5 empty] | Attended AZGS webinar: HUBS - Data and Serving Data. | KY HUB provided services to host data posted by LA. |  |  | Acquired and installed new storage drive for storing regional hub data | Running two servers that mirror each other, using F5 hardware for load balancing, fail over. Data is on a shared SAN, SAN is backed up nightly. | Participated in a webinar to discuss HUB workshops. |  |  |  | KGS co-hosted a workshop with the IGS
[10 empty] | HUB meeting in Arizona in Sept. Focus on planning for sustainability with server architecture. |  |  |  |  | Attended a workshop hosted by the Virginia Geological Survey. Gave a presentation on KY HUB role.
NV HUB |  |  | GIS Manager worked on the architecture of the network and data system. |  | Work continues to fully establish the Western Hub | HUBs meeting in early August to discuss expectations, protocols, and sustainability of the network. Extensive training on network components and network backup protocols were discussed. |  |  | Data from ID, NV, OR, and WA added to map services. Search capabilities added and data acquisition was programmed. New interactive map features data hosted by the NV HUB. | Updated the functionality of the NV HUB web application. Added data from WY not on the Web application. |  |  | Added web services for ID, NV, UT and MT. Purchased the new server and installed Web services software. Installed backup software. Created a virtual server. Maintained the web services. | Server down due to power outages at the university on June 18th , spent the remainder of the month setting up the new server’s virtual server (WEB3VM). Restored the NV HUB's Server after power outage. Moved all data to the new server and started installing new web services. | Continued work on a virtual server. Maintained web services. Continue to update the main server and the virtual server. Continued updating web applications. |  | Budget period has been extended to December 31, 2014 to maintain services at the HUBs.
[5 empty] | Attended AZGS webinar: HUBS - Data and Serving Data. |  |  |  |  | Running a used server, not heavily loaded. No backup. Data put in file geodatabases for each state. |  |  | Regional workshop at the Grand Sierra Resort in Reno, NV | Updated States data and services. | Updated States data and services. Added 30 new or appended datasets for CO, ID, MT, NV, SD, UT, WY for a total of 40 services.
Worked with AZGS to create replication from the NV HUB and AZGS. Tested replication. (Completed and submitted).