## Slide 1: NGDS Sprint Planning What we did
Created “Epics” based on use cases Requirements Document and Steve’s suggestions
      Epics group Use cases into a high level story and are useful in sprint planning
Prioritized Epics based on our own assumptions
Create Sprint Plan
    Based on the Prioritized Epics and our own guess about what follows what
    Added Stabilization Sprints
  Made effort estimations based on
    Functional description of the epics
    We broke the effort estimates into Testing, UI Design and Implementation, Server Side Implementation, Architecture (Design, investigation and documentation)
    Stabilization sprints have efforts of 500 or 100 Hours
  We found that by September we could have
      A Basic NGDS built with CKAN (See next slide for the feature list)
      Initial user feedback and integration into NGDS (However, note that the agile process encourages that each sprint has feedback from stakeholders)
      Documentation

## Slide 2: NGDS Sprint Planning NGDS Feature List
Upload Tier 1 and Tier 3 data (Tier 2 data treated same as Tier 1 data)
Multi file Upload
Initial Content Model
Manual Entry of Metadata and Simple Validation of metadata input
Harvesting of Metadata
Map Based Search
Library Based Search
Faceted Search
Download of Identified resource data file
User Management and basic functional access security based on user group membership
Basic security of resource lists

## Slide 3: NGDS Sprint Planning Other work we plan to do
Stanford Paper and Conference
Planning and running User Feedback sessions
Documentation of architecture and design decisions

## Slide 4: NGDS Sprint Planning What is missing?
In general, all of the “tasks” have been put into our Sprint Backlog. These tasks can be added as part of sprint planning done at the start of a sprint.
        But adding tasks will likely push our planned tasks off the planned delivery
        Also simply adding a task from the backlog might not be feasible because of where we are in the development (i.e. there are dependencies).
Here are some things that are “missing” based on the current funding:
      Ratings/ Social Networking
      Full text indexing
      Internationalization
      Thesaurus
      Adding various third party information such as land ownership, power lines, etc.

## Slide 5: NGDS Sprint Planning Timeline (To be continued on to the next page)
We plan Three Week Sprints
Sprints 2 & 3 (1/9/2013 - > 2/20/2013)
    Epic 001 Implement NGDS core functionality in the most basic way
    Total Effort 1330 hours
Sprints 4 & 5 (2/20/2013 -> 4/3/2013)
    Epic 004 Implement map-based searching and implement structured data upload
    Stanford paper and presentation
    Total Effort 1200 hours
Sprint 6 (4/3/2013 ->4/24/2013)
    Stabilization Cleanup, Improvements, Bug Fixes
    Total Effort 1000 hours
Sprint 7 (4/24/2013 -> 5/15/2013)
      Epic 5 and Epic 6 Update an uploaded file and user administration.
      Total Effort 320 hours

## Slide 6: NGDS Sprint Planning Timeline (Continue)
Sprint 8 (5/15/2013 -> 6/5/2013)
    Epic 7 and Epic 8 Data Security: Manage access rights to datasets and system administration
    Total Effort 540 hours
Sprint 9 (6/5/2013 - > 6/26/2013)
    Incorporate User session Feedback into NGDS
    Total Effort 1360 hours
Sprints 10 & 11 (6/26/2013 -> 8/7/2013)
    Epic 009 Faceted Search
    Total Effort 1420 hours
Sprint 9 (8/7/2013 ->8/28/2013)
    Cleanup, Improvements, Bug Fixes, Documentation
    Total Effort 500 hours